## Sheet1
Task | Start Week | Duration Weeks
Project Initiation | 1 | 1
Design & Development | 2 | 4
Testing | 6 | 2
Deployment | 8 | 1
Training & Go-Live | 9 | 1
Project Closure | 10 | 1